## Dashboard
World of Weddingz production readiness
As of 2026-10-05. Counts link to the canonical CSV registers included in the production repository.
Work items | Count |  | Readiness | Count | Status | Count
Total | 33 |  | P0 items not done | 21 | Open | 27
Open | 27 |  | Open release gates | 11 | In Progress | 0
In Progress | 0 |  | Open risks | 10 | PR Open | 3
PR Open | 3 |  | P0 open risks | 9 | Blocked | 1
Blocked | 1 |  | Approved requirements | 22 | Done | 2
Done | 2
Launch gate | Current state | Owner | Evidence needed | Rule
Repository foundation | Complete | Codex | Public visibility, protected main and native security controls verified | Reassess only if repository visibility changes
Railway candidate | Not Started | Unassigned | Security, S3, observability, capacity and all-role tests | No production domain yet
Railway public beta | Blocked | Product owner | GATE-002 through GATE-007 approved | Attach domain only here
AWS migration | Blocked | Product owner | Successful and rollback rehearsals plus budget/MFA/backup gates | Enable real executor last

## Open Items
Production open items
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
ID | Title | Phase | Type | Priority | Status | Owner | DependsOn | Acceptance | SourceRef | GitHubIssue | PR | LastUpdated
SEC-001 | Align authentication with Zoho SSO and multi-identifier login policy | Public beta safety | Security | P0 | PR Open | Codex |  | Administrators use Zoho SSO; existing users may use Zoho SSO or username/email/mobile plus password; OTP is verification/recovery only; unsafe public provider combinations fail startup | Production plan Task 1A and user authentication decision | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/6 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/58 | 2026-10-05
SEC-002 | Authorize and constrain WebSocket traffic | Public beta safety | Security | P0 | Open | Unassigned | SEC-001 | Origins and tokens are verified; calls and presence are relationship-scoped | Production plan Task 1B | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/7 |  | 2026-10-04
OPS-001 | Serialize replicated outbox and scheduled jobs | Public beta safety | Reliability | P0 | Open | Unassigned |  | Two workers cannot execute the same notification/payment job | Production plan Task 1C | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/8 |  | 2026-10-04
SEC-003 | Harden HTTP startup and migration integrity | Public beta safety | Security | P0 | Open | Unassigned |  | Security headers and private Swagger are enforced; migration sequence is unique and upgrade-safe | Production plan Task 1D | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/9 |  | 2026-10-04
DEP-001 | Remediate production dependency vulnerabilities | Public beta safety | Security | P0 | PR Open | Codex |  | No unaccepted critical/high runtime advisory; CI blocks regressions; explicitly documented no-fix build-tool exceptions remain narrow and reviewable | Production plan Task 1E | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/10 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/59 | 2026-10-05
OBS-001 | Implement backend structured observability | Observability | Platform | P0 | Open | Unassigned | SEC-003 | Correlated redacted API and worker logs pass tests | backend-observability-foundation plan | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/11 |  | 2026-10-04
OBS-002 | Implement client error intake | Observability | Platform | P1 | Open | Unassigned | OBS-001 | Sanitized browser/mobile failures correlate with backend requests | client-error-observability plan | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/12 |  | 2026-10-04
OBS-003 | Deploy local Loki Grafana and 30-day log archive | Observability | Platform | P0 | Open | Unassigned | OBS-001 | Local JSONL and Loki retain searchable logs for 30 days | local-log-platform plan | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/13 |  | 2026-10-04
CFG-001 | Create canonical non-secret platform configuration | Railway foundation | Configuration | P0 | Open | Unassigned | SEC-001 | One typed YAML file owns defaults; secrets remain outside Git; unknown keys fail | Production plan Task 3 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/14 |  | 2026-10-04
RLY-001 | Define four-service Railway Hobby deployment | Railway foundation | Infrastructure | P0 | Open | Unassigned | CFG-001 | Frontend API PostgreSQL and Redis pass cross-origin auth and WebSocket smoke tests | Production plan Task 4 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/15 |  | 2026-10-04
S3-001 | Provision private S3 media bootstrap | Railway foundation | Infrastructure | P0 | Open | Unassigned | CFG-001 | Real uploads use private encrypted versioned S3 and survive redeploys | Production plan Task 5 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/16 |  | 2026-10-04
OPS-002 | Collect capacity and cost snapshots | Operations | Backend | P1 | Open | Unassigned | CFG-001,OBS-001 | Exact account DAU request latency error resource database and cost measurements persist | Production plan Task 6 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/17 |  | 2026-10-04
OPS-003 | Deliver deduplicated operational alerts | Operations | Backend | P1 | Open | Unassigned | OPS-002 | Warnings and critical alerts reach portal email audit and logs without flooding | Production plan Task 7 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/18 |  | 2026-10-04
UI-001 | Build administrator Infrastructure dashboard | Operations | Frontend | P1 | Open | Unassigned | OPS-003 | Admin sees exact values thresholds evidence alert status and migration readiness | Production plan Task 8 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/19 |  | 2026-10-04
AUTH-001 | Add scoped administrator fresh-authentication step-up | Migration control | Security | P0 | Open | Unassigned | SEC-001,CFG-001 | Fresh Zoho reauthentication issues a five-minute single-use action-scoped token for migration start; application TOTP is a documented fallback only | Production plan Task 9 and user authentication decision | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/20 |  | 2026-10-05
MIG-001 | Implement migration state machine and mock executor | Migration control | Backend | P0 | Open | Unassigned | AUTH-001,OPS-002 | Mock runs every state/failure without external side effects; only one run is active | Production plan Task 10 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/21 |  | 2026-10-04
MIG-002 | Build admin migration timeline and confirmation | Migration control | Frontend | P1 | Open | Unassigned | MIG-001 | One protected action displays cost backup read-only window rollback boundary and live state | Production plan Task 11 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/22 |  | 2026-10-04
AWS-001 | Complete AWS Option B Terraform | AWS readiness | Infrastructure | P0 | Open | Unassigned | CFG-001,S3-001 | Disposable three-AZ EKS Aurora Redis edge security and monitoring environment passes policy tests | Production plan Task 12 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/23 |  | 2026-10-04
MIG-003 | Implement GitHub OIDC migration dispatcher | AWS readiness | Infrastructure | P0 | Open | Unassigned | MIG-001,AWS-001 | Signed replay-protected callbacks drive the real executor without static AWS keys | Production plan Task 13 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/24 |  | 2026-10-04
MIG-004 | Implement verified PostgreSQL synchronization and cutover | AWS readiness | Data | P0 | Open | Unassigned | MIG-003 | Counts sequences and critical checksums match; 15-minute failure restores Railway | Production plan Task 14 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/25 |  | 2026-10-04
QA-001 | Measure Railway capacity with representative load | Certification | Quality | P0 | Open | Unassigned | RLY-001 | Published operating thresholds retain at least 30 percent headroom | Production plan Task 15 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/26 |  | 2026-10-04
QA-002 | Rehearse successful AWS migration | Certification | Quality | P0 | Open | Unassigned | MIG-004,QA-001 | Sanitized production-sized dataset migrates and all critical journeys pass | Production plan Task 16 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/27 |  | 2026-10-04
QA-003 | Rehearse automatic rollback | Certification | Quality | P0 | Open | Unassigned | MIG-004 | Failures before and after DNS but before AWS writes restore Railway without split brain | Production plan Task 16 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/28 |  | 2026-10-04
REL-001 | Launch Railway public beta | Release | Release | P0 | Open | Unassigned | SEC-001,SEC-002,OPS-001,SEC-003,DEP-001,OBS-003,CFG-001,RLY-001,S3-001,QA-001 | All public-beta gates and live all-role tests pass before domain attachment | Production plan Task 17 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/29 |  | 2026-10-04
REL-002 | Enable real AWS migration action | Release | Release | P1 | Open | Unassigned | QA-002,QA-003 | Real executor remains disabled until rehearsal budget backup MFA and infrastructure gates are green | Production plan final gate | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/30 |  | 2026-10-04
SYNC-001 | Review current uncommitted planner-client source change | Source intake | Change intake | P1 | Open | Unassigned |  | Classify and either integrate through a traced PR or reject with reason | Current WOW working tree mobile/src/app/planner-clients.tsx | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/31 |  | 2026-10-04
SYNC-002 | Continuously review committed WOW-MD functional changes | Source intake | Change intake | P1 | Blocked | Product owner | GOV-002 | Every new source commit is classified and accepted changes have production PRs | Source integration policy | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/32 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/55 | 2026-10-04
QA-004 | Replace stale public and registration Playwright locators | Public beta safety | Quality | P1 | Open | Unassigned |  | Legacy two failures are updated to current accessible contracts and pass | QA findings F-002 F-003 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/33 |  | 2026-10-04
REL-003 | Embed deployment revision and provenance | Public beta safety | Release | P0 | Open | Unassigned | CFG-001 | Health and deployed UI identify the exact commit/image/config digest | QA finding F-001 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/34 |  | 2026-10-04
INT-001 | Define live integration onboarding gates | Post-beta | Integration | P2 | Open | Unassigned | CFG-001 | Each provider has sandbox production secrets webhooks budget owner and contract tests | QA limit L-002 | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/35 |  | 2026-10-04
GOV-001 | Enable private-repository protection and security settings | Governance | Governance | P0 | Done | Codex |  | Main requires PR and checks; security scanners and private reporting are enabled | User request | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/36 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/54 | 2026-10-04
GOV-002 | Establish SDLC knowledge and tracking system | Governance | Governance | P0 | Done | Codex |  | Markdown CSV Excel issues PR protocol and Obsidian index are linked and verified | User request | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/37 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/49 | 2026-10-04
GOV-003 | Reconcile authentication and dependency tracking | Governance | Governance | P0 | PR Open | Codex | SEC-001,DEP-001 | Canonical registers workbook and operating guidance match the implemented authentication policy and dependency evidence | User request | https://github.com/RohithTadiparti/world-of-weddingz-production/issues/60 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/61 | 2026-10-05

## Requirements
Requirements traceability
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
ID | Requirement | Source | Priority | Verification | WorkItems | Status
REQ-DEPLOY-001 | Closed beta may use Railway Trial or Free but public launch must use Railway Hobby | Migration design | P0 | Deployment configuration and launch checklist | RLY-001 REL-001 | Approved
REQ-DEPLOY-002 | Attach the production domain only at the final Railway launch gate | User direction | P0 | DNS evidence and release gate | REL-001 | Approved
REQ-STORAGE-001 | All real user media uses private S3 from the first account | Migration design | P0 | S3 integration and privacy tests | S3-001 | Approved
REQ-CONFIG-001 | One committed non-secret configuration owns defaults and mock selections | Migration design | P0 | Loader tests and config-boundary CI | CFG-001 | Approved
REQ-SECRET-001 | Secrets remain outside Git and are stored in platform secret stores | Security policy | P0 | Secret scan and environment review | CFG-001,GOV-001 | Approved
REQ-ALERT-001 | Admins receive persistent portal and email warning/critical alerts | User direction | P0 | Alert delivery unit/E2E and mail evidence | OPS-002,OPS-003,UI-001 | Approved
REQ-ALERT-002 | Alerts use exact thresholds and deduplicate repeated observations | Migration design | P1 | Threshold and reminder tests | OPS-002,OPS-003 | Approved
REQ-MIG-001 | One protected administrator action starts migration to AWS Option B | User direction | P0 | Admin Playwright and audit evidence | AUTH-001,MIG-001,MIG-002 | Approved
REQ-MIG-002 | Migration runs outside Railway and survives source service loss | Migration design | P0 | Workflow interruption rehearsal | MIG-003 | Approved
REQ-MIG-003 | Business writes pause no longer than 15 minutes for final cutover | Migration design | P0 | Cutover timer and rollback rehearsal | MIG-004 QA-003 | Approved
REQ-MIG-004 | Automatic rollback is guaranteed before AWS writes are enabled | Migration design | P0 | Injected failure rehearsals | QA-003 | Approved
REQ-MIG-005 | Railway remains read-only for 72 hours and deletion is separately approved | Migration design | P0 | Runbook and release evidence | MIG-004,REL-002 | Approved
REQ-TRACE-001 | Every production task links requirement issue branch PR tests and evidence | User direction | P0 | Governance register validation | GOV-001,GOV-002 | Approved
REQ-SYNC-001 | Functional source-repository changes are individually reviewed and integrated | User direction | P1 | Change-intake and production PR | SYNC-002 | Approved
REQ-QA-001 | CI unit database E2E Playwright mobile security and IaC checks are mandatory | User direction | P0 | Required GitHub checks | GOV-001 | Approved
REQ-QA-002 | Database and UI values must match exactly after documented normalization | QA mandate | P0 | Reconciliation evidence | MIG-004 QA-002 | Approved
REQ-LOG-001 | Logs remain searchable locally and in Loki for 30 days | Logging decision | P0 | Retention and query tests | OBS-003 | Approved
REQ-REV-001 | AWS migration readiness reports INR 1.2M target and INR 1.5M preferred monthly net revenue | Migration design | P1 | Admin readiness UI test | UI-001 | Approved
REQ-AUTH-001 | Administrators authenticate through Zoho SSO and do not require routine application TOTP | User direction | P0 | Authentication integration tests and controlled Zoho sign-in evidence | SEC-001 | Approved
REQ-AUTH-002 | Existing users may sign in with Zoho SSO or username email or mobile plus password and any valid email provider is accepted | User direction | P0 | Backend frontend mobile and Playwright authentication tests | SEC-001 | Approved
REQ-AUTH-003 | OTP is used only for signup/contact verification and password recovery and never as passwordless login | User direction | P0 | Route inventory and authentication tests | SEC-001 | Approved
REQ-AUTH-004 | Zoho domain DNS sender mailbox SMTP application password and production OAuth callback are configured only at the final deployment gate | User direction | P0 | Final release checklist and controlled delivery/SSO evidence | SEC-001,REL-001 | Approved

## Test Inventory
Test coverage and evidence
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
ID | Layer | Scope | CurrentEvidence | CurrentResult | RequiredNextEvidence | WorkItems
QA-BASE-001 | Backend unit and service | 64 suites and 787 cases | QA workbook 2026-10-04 | 778 passed 9 skipped | All affected suites green on production repo | All implementation items
QA-BASE-002 | Database E2E | 51 cases on isolated PostgreSQL | QA workbook 2026-10-04 | 50 passed 1 skipped | Migration locking alert and cutover cases added | OPS-001 OPS-002 MIG-001 MIG-004
QA-BASE-003 | Live UI role navigation | 105 authenticated screens across 8 roles | QA workbook 2026-10-04 | 16 of 18 legacy tests plus replacement flows | Current locator suite green | QA-004
QA-BASE-004 | Fresh account lifecycle | Two six-role cohorts including recovery | QA workbook 2026-10-04 | 16 of 16 passed | Repeat on Railway candidate | REL-001
QA-BASE-005 | Wedding lifecycle | Self-managed planner-assisted shared task and release | QA workbook 2026-10-04 | 3 of 3 passed | Repeat on Railway and AWS rehearsal | REL-001 QA-002
QA-BASE-006 | Database to UI reconciliation | 46 exact comparisons | QA workbook 2026-10-04 | 46 matched | Automated source-target and UI reconciliation | MIG-004 QA-002
QA-BASE-007 | API inventory | 426 Swagger operations | QA workbook 2026-10-04 | Inventory complete with execution backlog | Permission/state matrix for critical operations | All API-changing items
QA-SEC-001 | Security | Admin MFA provider startup WebSockets headers secrets dependencies | SEC-001 PR 56 and merged WOW-MD PR 37 | Provider policy 6 of 6; admin auth/JWT 49 of 49; source mirror 55 of 55; protected source and production CI passed | Complete live staged enrollment and Zoho delivery smoke evidence | SEC-001 SEC-002 SEC-003 DEP-001 GOV-001
QA-PERF-001 | Performance | Railway ramp spike soak recovery | None | Not run | Measured limits with 30 percent headroom | QA-001
QA-RES-001 | Resilience | Backup restore and failed cutover | None | Not run | Successful restore and two rollback rehearsals | QA-002 QA-003
QA-GOV-001 | Source synchronization | Private-source report and shared-code mirror gate | PR 55 local evidence | 19 of 19 governance and synchronization tests passed | Configure WOW_SYNC_TOKEN and capture first scheduled artifact | SYNC-002

## Risks
Production risks
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
ID | Risk | Impact | Likelihood | Priority | Mitigation | Owner | Status | Evidence
RISK-001 | Public beta exposes real PII before security blockers close | Critical | Possible | P0 | Block domain launch on security release gates | Unassigned | Open
RISK-002 | Free or hard spending limit stops Railway workloads | High | Possible | P0 | Use Hobby for public launch and alert before hard limit | Unassigned | Open
RISK-003 | Railway memory is insufficient for the backend | High | Possible | P0 | Measure idle/load use and retain 30 percent headroom | Unassigned | Open
RISK-004 | Public or missing S3 objects expose or lose user media | Critical | Possible | P0 | Private bucket least privilege reconciliation and restore test | Unassigned | Open
RISK-005 | Duplicate jobs send or release money twice | Critical | Possible | P0 | Database claims locks and idempotency tests | Unassigned | Open
RISK-006 | Migration produces split-brain writes | Critical | Unlikely | P0 | Read-only final sync and no rollback after AWS writes without reverse replication | Unassigned | Open
RISK-007 | DNS cutover fails after source is paused | High | Possible | P0 | Preflight DNS access TTL and automatic restoration rehearsal | Unassigned | Open
RISK-008 | Source and production repositories drift silently | High | Likely | P1 | Scheduled drift report and change-intake register | Unassigned | Open
RISK-009 | Mock integration appears to deliver real email/payment/identity outcome | High | Possible | P0 | Explicit simulated state and production fail-closed validation | Unassigned | Open
RISK-010 | Historical secrets enter the private production history | Critical | Possible | P0 | Clean snapshot history secret scanning and push protection | Codex | Mitigated | Initial scan found no tracked high-confidence signatures
RISK-011 | Private repository cannot enforce native branch protection or secret scanning on the current GitHub plan | High | Certain | P0 | Temporarily use public visibility with protected main and native security controls; return private only on an eligible tier | Product owner | Mitigated | Public visibility and controls enabled through GOV-001 on 2026-10-04
RISK-012 | Public source exposes architecture test conventions and historical development-only credentials | High | Possible | P0 | Remove fallback credentials; keep real secrets and PII outside Git; require push protection Gitleaks and native scanning | Security | Mitigated | Tracked history scanned; seed fallback removed in GOV-001; test and production credentials require external stores
RISK-013 | Public deployment tier is enabled before Zoho SSO and administrator recovery are proven | High | Possible | P0 | Verify exact OAuth client callback administrator matching-email login Zoho-account MFA and a documented recovery owner in restricted staging before public-beta | Security | Open | SEC-001 PR 58 implements Zoho-only administrator login; production Zoho configuration is intentionally deferred to the final gate
RISK-014 | Framework and mobile build-tool dependency advisories remain after runtime remediation | High | Possible | P0 | Block new critical/high runtime advisories; allow only four exact no-fix Expo advisory IDs; schedule Nest major migration and review exceptions each release | Security | Mitigated | DEP-001 PR 59 records zero critical/high backend runtime advisories zero frontend advisories and the exact mobile exception set

## Access
Account and access readiness
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
ID | System | AccessNeeded | HumanOwner | MachineIdentity | SecretLocation | Status | VerifiedDate | Notes
ACC-001 | GitHub | Public repository admin and Actions environments | RohithTadiparti | GitHub Actions token | Github platform | Available | 2026-10-04 | Public visibility; protected main; native secret scanning and push protection enabled
ACC-002 | Railway | Project owner deploy variables domains usage and rollback | To be confirmed | Later project token | GitHub railway-beta environment | Pending |  | Do not create production domain until final gate
ACC-003 | AWS root | Ownership billing recovery and MFA | To be confirmed | None | AWS account | Pending |  | No routine root use
ACC-004 | AWS administrator | Identity Center or role for bootstrap IAM S3 KMS budgets and OIDC | To be confirmed | GitHub bootstrap OIDC role | AWS and GitHub environments | Pending |  | Prefer SSO and OIDC over access keys
ACC-005 | AWS S3 runtime | Media-prefix object access only | To be confirmed | Railway runtime principal | Railway variables | Pending |  | No bucket admin permissions
ACC-006 | DNS provider | Zone read and DNS edit for production domain | To be confirmed | Scoped DNS token | GitHub production environment | Pending |  | No global API key
ACC-007 | Operational email | Zoho domain mailbox DNS authentication reports and app-password rotation | To be confirmed | Zoho SMTP identity | GitHub Railway or Kubernetes secrets | Approved candidate |  | Low-volume beta only; owner must configure domain MFA app password and first delivery evidence
ACC-008 | Payment provider | Razorpay sandbox then production account | To be confirmed | Webhook/API credentials | Protected secret store | Deferred |  | Separate onboarding gate
ACC-009 | SMS WhatsApp push identity | Provider sandbox then production accounts | To be confirmed | Provider credentials | Protected secret store | Deferred |  | Separate onboarding gates
ACC-010 | WOW-MD source review | Private repository contents read for scheduled change reports | RohithTadiparti | Fine-grained WOW_SYNC_TOKEN | Production GitHub Actions secret | Pending |  | Scope only to WOW-MD Contents read; rotate within 90 days

## Release Gates
Release gates
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
ID | Gate | Environment | RequiredEvidence | Status | Owner | Evidence | ApprovedDate
GATE-001 | Source baseline and secret scan | Repository | Clean-history baseline and secret scan | Complete | Codex | Initial repository setup 2026-10-04 | 2026-10-04
GATE-002 | Required CI and security checks | Repository | Green lint typecheck unit E2E build CodeQL dependency secret and IaC checks | Open | Unassigned
GATE-003 | Public-beta security blockers | Railway candidate | SEC-001 SEC-002 OPS-001 SEC-003 DEP-001 closed | Open | Unassigned
GATE-004 | Observability and backup restore | Railway candidate | 30-day logs alerts backup and successful restore | Open | Unassigned
GATE-005 | Private S3 media | Railway candidate | Privacy persistence reconciliation and recovery evidence | Open | Unassigned
GATE-006 | Railway capacity | Railway candidate | Load report with 30 percent headroom | Open | Unassigned
GATE-007 | All-role release tests | Railway candidate | Current Playwright account wedding API and DB comparison evidence | Open | Unassigned
GATE-008 | Production domain attachment | Railway public | GATE-002 through GATE-007 approved | Open | Product owner
GATE-009 | AWS successful migration rehearsal | AWS rehearsal | Exact reconciliation all journeys and observation pass | Open | Unassigned
GATE-010 | AWS rollback rehearsal | AWS rehearsal | Before-DNS and after-DNS rollback evidence | Open | Unassigned
GATE-011 | Real migration executor enablement | Production | AWS budget MFA backup Terraform and rehearsals green | Open | Product owner
GATE-012 | Railway decommission | Production | 72-hour stable AWS operation and separate approval | Open | Product owner

## Change Intake
Source change intake
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
ID | SourceRepository | SourceCommit | SourcePath | Classification | Decision | ProductionItem | ProductionPR | ReviewedBy | ReviewedDate | Notes
CHG-001 | RohithTadiparti/WOW-MD | UNCOMMITTED | mobile/src/app/planner-clients.tsx | Functional candidate | Review required | SYNC-001 |  |  | 2026-10-04 | Preserved in source working tree and not copied into baseline
CHG-002 | RohithTadiparti/WOW-MD | UNCOMMITTED | .gitignore | Repository hygiene | Review required | SYNC-001 |  |  | 2026-10-04 | Three ignored paths require review before adoption
CHG-003 | RohithTadiparti/WOW-MD | 07218b4..de7d8dd (LOCAL ONLY) | 37 committed paths | Functional UI candidates | Await source publication and per-commit review | SYNC-002 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/55 | Codex | 2026-10-04 | Local main is 21 commits ahead of origin; scheduled GitHub review intentionally sees pushed commits only

## PR Handoffs
Pull request handoffs
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
WorkItem | PR | Branch | BaseCommit | HeadCommit | SourceCommits | Tests | Deployment | Rollback | ResidualRisks | Status | Updated
GOV-002 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/49 | codex/gov-002-production-program | 1e9f458 | 4444b86 | 07218b4ab02a8702a4d8d9fdab7dc26e579ab7b4 | Final PR head 4444b86: backend build/test pass; frontend pass; mobile pass; Docker build pass; registers pass; Gitleaks pass; CodeQL JavaScript/TypeScript and Actions pass with 30-day SARIF artifacts; local governance 4/4 | Documentation and governance only; no Railway deployment | Revert PR 49; bootstrap remains clean source snapshot | GitHub plan blocks protected private branches native secret scanning and native CodeQL upload; offline SARIF and CI Gitleaks compensate; tracked by GOV-001 | Ready to Merge | 2026-10-04
GOV-001 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/54 | codex/gov-001-public-protection | 922cfee | 152f4d3 |  | Final PR head 152f4d3: backend E2E and tests pass; frontend pass; mobile pass; Docker pass; registers pass; Gitleaks pass; native CodeQL JavaScript/TypeScript and Actions pass; seed config 3/3; governance 7/7 | GitHub visibility and protection settings plus repository security configuration; no application deploy | Change visibility/settings separately and revert PR; never restore fallback credential | Public source and historical development credential; 83 dependency alerts | Ready to Merge | 2026-10-04
SEC-001 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/58 | codex/sec-001-sso-login-policy | 29537ee | 8e7f3e8 | WOW-MD PR 38 head 29ee273 | Backend typecheck and 55 focused auth/config tests pass; frontend typecheck and 173 tests pass; mobile typecheck passes; production and source protected CI application jobs pass | At the final release gate configure exact Zoho OAuth client/callback domain SPF DKIM DMARC sender mailbox and SMTP application password; then run controlled admin/non-admin SSO and email tests | Restore the prior image/config and disable Zoho SSO; do not enable passwordless OTP or log-based mail in public tier | Production Zoho credentials/DNS and live-provider evidence are intentionally deferred; the aggregate CodeQL status on production PR is failing despite both analysis jobs passing and needs repository-level triage | PR Open | 2026-10-05
SYNC-002 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/55 | codex/sync-002-gated-source-review | 57e13d0 | 422cbc4 | 07218b4..de7d8dd local review only | Protected PR checks passed: build-and-test frontend mobile docker-build registers secrets CodeQL JavaScript/TypeScript and Actions; local source report found 21 commits and 37 paths with zero dependency or unsafe paths | Add read-only WOW_SYNC_TOKEN then run the scheduled workflow once; no application or hosting deployment | Revert PR 55 and remove WOW_SYNC_TOKEN; source and production histories remain unchanged | Private-source token is not configured; local/unpushed source commits remain intentionally invisible to GitHub Actions | Blocked | 2026-10-04
DEP-001 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/59 | codex/dep-001-dependency-remediation | 29537ee | 1ecbfdf | WOW-MD PR 39 head d8ef995 | Backend clean install typecheck lint build and 792 tests pass with 9 skipped; frontend clean install typecheck 173 tests build and 10 Playwright flows pass; runtime audits: backend 0 critical/0 high frontend 0; exact-ID mobile gate passes; production and source protected CI pass | No deployment before review and merge; after merge let GitHub rescan manifests and confirm alert counts and audit gates on main | Revert PR 59; restore prior lockfiles and packages; retain the audit report for comparison | Backend moderate/low build-tool advisories and four exact no-fix Expo advisory roots remain; forced NestJS 12 and Expo downgrades were tested and rejected as unsafe | PR Open | 2026-10-05
GOV-003 | https://github.com/RohithTadiparti/world-of-weddingz-production/pull/61 | codex/gov-003-auth-dependency-tracking | 29537ee | 1235cd3 | SEC-001 PR 58 and DEP-001 PR 59 evidence only | Register validator workbook regeneration and formula-error scan pass; dashboard visually reviewed | Governance and documentation only; no application or hosting deployment | Revert PR 61; implementation PRs and their evidence remain unchanged | Implementation PRs still require review/merge and GitHub rescan; Zoho live configuration remains a final release gate | PR Open | 2026-10-05

## Documents
Document register
Generated from docs/tracking/registers. Update the CSV register, then regenerate this workbook.
ID | Document | Path | Owner | Status | ReviewCadence | LastReviewed | RelatedItems
DOC-001 | Production program | PRODUCTION_PROGRAM.md | Product and engineering | Active | Each release | 2026-10-04 | All
DOC-002 | Knowledge matrix index | docs/knowledge-matrix/README.md | Engineering | Active | Monthly | 2026-10-04 | GOV-002
DOC-003 | SDLC operating model | docs/knowledge-matrix/sdlc.md | Engineering | Active | Quarterly | 2026-10-04 | GOV-002
DOC-004 | Account and access matrix | docs/knowledge-matrix/access-matrix.md | Security and operations | Draft | Monthly | 2026-10-04 | GOV-001
DOC-005 | Test strategy | docs/knowledge-matrix/test-strategy.md | Quality | Active | Each release | 2026-10-04 | QA-001 QA-002 QA-003
DOC-006 | Railway and AWS migration design | docs/superpowers/specs/2026-10-04-railway-first-aws-migration-design.md | Architecture | Draft | On decision change | 2026-10-04 | REL-001 REL-002
DOC-007 | Implementation plan | docs/superpowers/plans/2026-10-04-railway-first-aws-migration.md | Engineering | Active | Weekly | 2026-10-04 | All
DOC-008 | Task and PR handoff protocol | docs/governance/LLM_TASK_PROTOCOL.md | Engineering | Active | Quarterly | 2026-10-04 | GOV-002
DOC-009 | Source integration process | docs/governance/source-integration.md | Release engineering | Active | Each source review | 2026-10-04 | SYNC-001 SYNC-002
DOC-010 | Contributing rules | docs/governance/CONTRIBUTING.md | Engineering | Active | Quarterly | 2026-10-04 | GOV-001
DOC-011 | Baseline QA evidence | docs/evidence/qa/WOW_End_to_End_QA_Report_2026-10-04.xlsx | Quality | Baseline | Immutable | 2026-10-04 | QA-004 REL-003
DOC-012 | Production tracking workbook | docs/tracking/production-readiness-tracker.xlsx | Program management | Generated | Each change | 2026-10-04 | GOV-002
DOC-013 | Gated source synchronization plan | docs/superpowers/plans/2026-10-04-gated-source-synchronization.md | Release engineering | Active | On synchronization policy change | 2026-10-04 | SYNC-002
DOC-014 | SEC-001 implementation plan | docs/superpowers/plans/2026-10-04-sec-001-admin-mfa-provider-policy.md | Security | Active | On authentication/provider policy change | 2026-10-04 | SEC-001
DOC-015 | Zoho SSO and mail operating guide | docs/operations/zoho-mail.md | Security and operations | Approved candidate | Quarterly or provider change | 2026-10-05 | SEC-001 AUTH-001 OPS-003
DOC-016 | Dependency remediation record | docs/security/dependency-remediation-2026-10-04.md | Security | Approved candidate | Each dependency change | 2026-10-05 | DEP-001